## Marketing
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 0.78
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 1
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 0.45
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0

## Product Dev
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 1
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 0.78
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0

## Customer Service
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 1
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 1
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0